## Sheet1 (hidden)
Annexure No.1
Rural Infrastructure Development Programme - 2017
Physical and Financial Progress of the Month of …………………………2017
Divisional Secretariate Division (a) |  | Name: …………………………….
No:………………………………..
SN | Name of Project | G.N.Division (b) |  | Sector | Type of Project (Construction /Goods & Services) | Total Estimate Cost (Rs.) |  | BID AMOUNT | Allocation (Rs.) | Expenditure (Rs.) | Unit of Measure | Physical progress (c ) | [9 empty] | No of Beneficiaries | Remarks
|  | Name | No |  |  | With VAT | Without VAT |  |  |  |  | A | B |  |  |  | C | D | E | F | G
[13 empty] | B1 | B2 | B3 | B4
1 | Construction of culvert at Mrs. Indrani's Houes Road | 606 Manathu | 10320 | RA | Construction |  | 353459.13 |  | 346500 |  | 41m
2 | 1. Construction of Culvert at Buddigaminipura Main Road - Near the Mrs. Chandani & Mr. Binat House | 607 Palavi | 10339 | RA | Construction |  | 353170.1 |  | 346500
2. Construction of Box culvert at Mrs. Indrani's Houes Road
3 | Construction of culverts at Attavilluwa 1 st Lane | 607 A Attavilluwa | 10338 | RA | Construction |  | 359183.68 | 345590.6 | 346500
4 | Donating Ro water Filter for Central Attavilluwa & North Attavilluwa Primary School | 607 B Central Attavilluwa | 10341 | RA | Good & Services
5 | Concreeting Mr.Marasingha's House Road at Samagi Lane | 607 C Bodirajapura | 10337 | RA | Construction |  | 352853.32 | 341550 | 346500 |  | 48 m
6 | Concreeting 1st Culvert at Kajugaha Lane to Maha Aela Road | 607 D Poththuwilluwa | 10340 | RA | Construction |  | 501037.4 | 450290 | 495000
7 | Donating & Repair Computer for Manaweriya Primary School | 615 Sellakandal | 10322 |  | Good & Services
8 | Completing Balance Work at 6 th Mile Post Community Hall at Kalladiya | 615 A Kalladiya | 10336 | OIP | Construction |  | 348969.5
9 | Construction of box culvert at near yhe Maduragama Lakdanau | 615 B Thammennagama | 10335 |  | Construction |  | 438721.76 | 460120 | 455400
10 | Concreeting Mr. Udaya Kumara's House Road | 615 C Nelumvewa | 10323 | RA | Construction |  | 352850.52 | 409645 | 346500
11 | Concreeting left bound 1 st cannal | 615 D Sirambiyadiya | 10321 | RA | Construction |  | 349228.4
12 | Concreeting Balance Work at Abeyapura by Road of Temple | 616 Senakudirippuwa | 10328 | RA | Construction |  | 441542.55 | 499570 | 435600 |  | 61m
13 | Concrtteing internal Lanes | 617 Puttaalam North | 10332 | RA | Construction |  |  | 404665 | 346500 |  | m
14 | Concreeting Makkalpuram 2nd Lane | 617 A Mullipuram | 10325 | RA | Construction |  | 350244.84
15 | Completing Balance Work at Manalgundu Community Hall | 617 B Puttalam East | 10327 | OIP | Construction |  | 501943.76
16 | Concreeting Road at infrond of Pariappapalliyadi GS Office | 617 C Marikkar Street | 10324 | RA | Construction |  | 353244.71 | 408320 | 346500 |  | 47m
17 | Concreeting K.K. Street | 617 D Old Jumma Mosque | 10331 | RA | Construction |  | 359006.1 | 419175 | 346500 |  | 55m
18 | Construction Drain at 2nd Lane to Ibunubathutha Road | 617B Periyapallikudirippu | 10333 | RA | Construction |  | 364236.58 | 410720 | 346500
19 | Construction Drain at Mujahideen tempal Road | 617 F Pudukudirippu | 10326 | RA | Construction |  | 362363.38 | 470565 | 346500
20 | Construction Balance Work at Community Hall | 618 Puttalam South | 10330 | OIP | Construction |  | 352951
21 | Re Construction of Anapulluththua Community Hall | 618 A Thilladiya | 10329 | OIP | Construction |  | 360862.3
22 | Retaining wall at near the Colourcon tile factry , Arafa nagar lane | 618 B Rathmalyaya | 10334 | RA | Construction |  | 348003.25 |  | 346500 |  | 14m
(a) - Please see the Annexure No.3 for Divisional Secretariate Divisions Names & Nos
(b) - Please see the Annexure No.4 for Grama Niladhari Divisions Names & Nos
(c ) - Instructions to fill the Physical Progress
| Description for rating |  |  |  | Rates | Percentage Ranges
| Estimate is being / to be prepared and initial works started |  |  |  | A | (0 - 5)%
| Constructions: B - 1 = Estimates approved / Bid documents prepared, B - 2 = Quotation / Bid called B - 3 = Quotation / Bid Received B - 4 = Contract Awarded. (25% completed) Other : Identified Institutions / CBO's to provide Goods/ Instruments Obtain required list of goods, Estimated prepared |  |  |  | B | (6 - 25)%
| Constructions : Started construction works , (40% completed) Other : Placed orders for goods / instruments |  |  |  | C | (26 - 40)%
| Constructions : 60% Completed Other : Received goods / instruments as per the order |  |  |  | D | (41 - 60)%
| Constructions : 80% Completed Other : Received goods / instruments as per the order |  |  |  | E | (61 - 80)%
| Constructions : 99% Completed Other : Completed lists of goods and beneficiaries |  |  |  | F | (81 - 99)%
| Constructions : 100% Completed Other : Issued goods and instruments to identified institutions/ CBOs |  |  |  | G | 100%
| Constructions : 99% Completed Other : Completed lists of goods and beneficiaries |  |  |  | F |  | (81 - 99)%
| Constructions : 100% Completed Other : Issued goods and instruments to identified institutions/ CBOs |  |  |  | G |  | 100%
E For Constructions Projects 51% - 75% completed
For Other Projects: Received goods /instruments as per the order
F - For Constructions 76% - 99% completed
For Other Projects: Completed lists of goods and beneficiaries
G For Constructions Projects 100% completed
For Other Projects: Issued goods and instruments to identified institutions / CBOs

## ඉතිරිය
ග්‍රාමීය යටිතල පහසුකම් සංවර්ධන වැඩසටහන - 2017
ඉතිරි මුදල් සඳහා නව ව්‍යාපෘති අනුමත කර ගැනීම
පුත්තලම ප්‍රාදේශීය ලේකම් කොට්ඨාසය | [9 empty] | DS Division : Puttalam
අ/අ | ග්‍රාම සේවා වසම | යටිතල පහසුකම් සංවර්ධන ව්‍යාපෘති යෝජනාව | අනුමත කරන ලද මුදල රු. | ඇස්තමේන්තු වටිනාකම රු. | අනුමත කරන ලද මුදල රු. | ගෙවීම් රු. | ගෙවීම් කිරීමෙන් හා ප්‍රසම්පාදන ක්‍රියාවලියෙන් පසු ඉතිරි වන මුදල රු. | භෞතික ප්‍රගතිය | [6 empty] | මූල්‍ය ප්‍රගතිය රු. | Remarks |  | Financial Progress(Rs) | කොන්ත්‍රාත් ආයතනය | Bid Amount | ඉතිර මුදල සඳහා යෝජිත ව්‍යාපෘතිය | ඇස්තමේන්තු සකස් කර ඇති/නැති බව | නව ව්‍යාපෘතියේ වටිනාකම රු. | ග්‍රාමීය කමිටුවෙන් එකඟතාවය ලැබී ඇති/නැති බව
[8 empty] | A | B | C | D | E | F | G
1 | 606 මනතිව් | ඉන්ද්‍රානි මියගේ නිවස මාර්ගය කාණු පද්ධතිය සකස් කිරීම | 353459.13 |  | 346500 | 339517.46 | 6982.54 | 41m | [8 empty] | 1 | 25 |  | 34.9127 | කිරල් ඔය ගොවි සමිති ශාලාවේ වහලය ඉදිකිරීම | නැත | 300000 | ඇත
2 | 607 පාලාවිය | 1. බුද්ධිගාමිණි පුර ප්‍රධාන පාර චාන්දනී මියගේ හා බිනට් ප්‍රනාන්දු මයාගේ නිවස අසල බොක්කු සකස් කිරීම | 353170.1 |  | 346500 | 330981.88 | 15518.12 | [9 empty] | 1 | 120 |  | 1697.5873
2. පාසල ඉදිරිපිට නදීකා මියගේ නිවස ඉදිරිපිට පාර පෙට්ටි බෝක්කුවක් ඉදිකිරීම
3 | 607 ඒ අට්ටවිල්ලුව | අට්ටවිල්ලුව පළමු බවුම මාර්ගයේ බෝක්කු 02 ක් ඉදිකිරීම | 359183.68 | 345590.6 | 346500 | 301568.83 | 44931.17 | [9 empty] | 1 | 132
4 | 607 බී මධ්‍යම අට්ටවිල්ලුව | මධ්‍යම අට්ටවිල්ලුව කනිෂ්ඨ විද්‍යාල සහ උත්තර අට්ටවිල්ලුව රජයේ විදුහල සඳහා RO water filter 02 ක් ලබා දීම | 395300 |  | 360000 | 395300 | -35300 | [8 empty] | 1 |  | 359
5 | 607 සී බෝධිරාජපුර | සමගි මාවත මාරසිංහ මයාගේ නිවස පාර කොන්ක්‍රීට් කිරීම | 352853.32 | 341550 | 346500 | 328706 | 17794 | 48 m | [8 empty] | 1 | 23 |  | 88.97
6 | 607 ඩී පොත්තුවිල්ලුව | පොත්තුවිල්ලුව කජුගහ හන්දියේ සිට මහ ඇළ දක්වා යන මාර්ගයේ පළමුවන බෝක්කුව පුළුල් කර කොන්ක්‍රීට් කිරීම | 501037.4 | 450290 | 495000 | 446779.83 | 48220.17 | [9 empty] | 1 | 75
7 | 615 සෙල්ලකන්දල් | මානාවේරිය කනිෂ්ඨ විදුහලේ පරිගණක අලුත්වැඩියාව හා මිල දී ගැනීම | 346500 |  | 350000 | 350000 | 0 | [9 empty] | 1 | 40 |  | 0
8 | 615 ඒ කල්අඩිය | 6 කණුව සමිති ශාලාවේ ඉතිරි වැඩ නිම කිරීම | 348969.5 |  | 346500 | 335761.28 | 10738.72 | [9 empty] | 1 | 175 |  | 53.6936
|  | බහුකාර්ය ගොඩනැගිල්ල |  |  | 313719.5
9 | 615 බී තම්මැන්නාගම | මදුරගම ප්‍රධාන මාර්ගයේ පෙට්ටි බෝක්කුවක් ඉදිකිරීම (ලක්දනව්ව අසල) | 438721.76 | 460120 | 455400 | 416767.23 | 38632.77 | [9 empty] | 1 | 45 |  | 193.1639
10 | 615 සී නෙළුම්වැව | උදය කුමාර මයාගේ නිවස මාර්ගය කොන්ක්‍රීට් කිරීම | 352850.52 | 409645 | 346500 | 344497.6 | 2002.4 | [9 empty] | 1 | 18 |  | 10.012
11 | 615 ඩී සිරම්බිඅඩිය | පාවට්ටමඩුව ගොවි ජනපද ව්‍යාපාරයේ වම් ඉවුර පළමු ඇළ කොන්ක්‍රීට් කිරීම. | 349228.4 |  | 346500 | 344204.45 | 2295.55 | [9 empty] | 1 | 45 |  | 11.4777
12 | 616 සේනකුඩිරිප්පුව | අභයපුර පන්සල අතුරු පාර ඉතිරි කොටස කොන්ක්‍රීට් කිරීම | 441542.55 | 499570 | 435600 | 434341.45 | 1258.55 | 61m | [8 empty] | 1 | 250 |  | 6.2927
13 | 617 පුත්තලම උතුර | පුත්තලම උතුර 3 වන හරස් වීදිය, 5 වන හරස් වීදිය හා මිහ්රාජ් මස්ජිද් ඉදිරිපිට මාර්ග ප්‍රතිසංස්කරණය කිරීම | 352534.65 | 404665 | 346500 | 298660.94 | 47839.06 | [9 empty] | 1 | 275 |  | 239.1953
14 | 617 ඒ මුල්ලිපුරම | මක්කල්පුරම් 2 වන පටුමග කොන්ක්‍රීට් කිරීම | 350244.84 |  | 346500 | 327569.5 | 18930.5 | [9 empty] | 1 | 45 |  | 94.6525
15 | 617 බී පුත්තලම නැගෙනහිර | මනල්ගුන්ඩුව ප්‍රජා ශාලාවේ ඉතිරි වැඩ නිම කිරීම | 501943.76 |  | 495000 | 451369.29 | 43630.71 | [9 empty] | 1 | 450 |  | 218.1536
16 | 617 සී මරික්කාර්වීදිය | පාරිඅප්පාපල්ලිඅඩිය ගම්මානයේ ග්‍රාම නිලධාරි කාර්යාලය ඉදිරිපිට මාර්ගය කොන්ක්‍රීට් කිරීම | 353244.71 | 408320 | 346500 | 343873.09 | 2626.91 | 47m | [8 empty] | 1 | 75 |  | 13.1345
17 | 617 ඩී පරණජුම්මාපල්ලිය | කේ.කේ. වීදිය කොන්ක්‍රීට් කිරීම | 359006.1 | 419175 | 346500 | 339662.34 | 6837.66 | 55m | [8 empty] | 1 | 85 |  | 34.1883
18 | 617 ඊ පෙරියපල්ලිකුඩිරිප්පු | 2 වන පටුමග සිට ඉබුනු බදූදා පාර කාණු පද්ධතිය සකස් කිරීම | 364236.58 | 410720 | 346500 | 344812.6 | 1687.4 | [9 empty] | 1 | 65 |  | 8.437
19 | 617 එප් පුදුකුඩිරිප්පුව | මුජාහිදීන් පල්ලිපාර කාණුව ඉදිකිරීම | 362363.38 | 470565 | 346500 | 339160.81 | 7339.19 | [9 empty] | 1 | 120 |  | 36.696
20 | 618 පුත්තලම දකුණ | පු/දකුණ අඩක් නිම කර ඇති පොදු සමිති ශාලාවේ ඉතිරි වැඩ නිම කිරීම | 352951 |  | 346500 | 346462.55 | 37.45 | [9 empty] | 1 | 175 |  | 0.18725
21 | 618 ඒ තිල්අඩිය | ආනපුලුඌත්තුව ප්‍රජා ශාලාව ප්‍රතිසංස්කරණය කිරීම | 360862.3 |  | 346500 | 323603.5 | 22896.5 | [9 empty] | 1 | 220 |  | 114.4825
22 | 618 බී රත්මල්යාය | රත්මල්යාය අර්ෆා නගර මාර්ගයේ සෝදාපාලුවට ලක්ව ඇති ස්ථානය ගල් ෆයිල් කර ගැල්වනයිස් දැල් ආවරණය කිරීම | 348003.25 |  | 346500 | 337679.87 | 8820.13 | 14m | [8 empty] | 1 | 120 |  | 44.1007
මුළු එකතුව |  |  | 8298206.93 |  | 8448719.5 | 7821280.5 | 313719.5 | [15 empty] | 300000
11000000